## Sheet1
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
Personel | Loss of team members | One or more team members drop the class | 2 | 4 | 4 | 32 | Team Leader | 2023-09-12 | Redefine the project scope if necessary, and assign the tasks to other team members. | Ok, Lauren was moved to team 7, Abdallah left the course | Closed
Security | Poor Session Management | Various session mismanagement vulnerabilities exist, including the session cookies lacking the Http-Only flag, and inadequate session invalidation. | 3 | 3 | 3 | 27 | Secuirty Leader | 2023-10-24 | Utilise proper session invalidation strategies. | Ok, adequate session management is implemented | Closed
Requirements | unclear requirements | Project requirements may be unclear or ambiguous | 4 | 3 | 3 | 18 | Requirement leader | 2023-10-24 | Collaborate with stakeholders to clarify requirements | Ok, ambigous requirements are discussed during meetings | Closed
Devops | Database failure | Database corruption or unavailability | 4 | 5 | 5 | 10 | Configuration leader | 2023-10-24 | Setup recovery strategy | Ok, cloud database has recovery and working well | Closed
Design and implementation | Improper design | Design choices may not align with project goals | 3 | 3 | 2 | 18 | Requirement leader | 2023-10-24 | Review and refine design, involve stakeholders | Ok, design aligns with project goals | Closed
Design and implementation | Messy code | Codebase may become disorganized and hard to maintain | 3 | 3 | 2 | 18 | Design leader | 2023-10-24 | Enforce coding standards, conduct code reviews | Ok, eslint and code reviews are helpful | Closed
Communication | worked on wrong components | Team members work on the wrong project components | 2 | 4 | 2 | 16 | Team Leader | 2023-10-24 | Improve project component tracking | Ok, functional and non functional requirements are met | Closed
Requirements | constant requirements changes | Frequent changes in project requirements | 4 | 4 | 3 | 12 | Requirement leader | 2023-10-24 | Implement a change request process, assess impact | Ok, functional and non functional requirements are met | Closed
Secuirty | Weak password | Predictable passwords can pose authentication vulnerabilities, making it easier for attackers to target specific users. | 3 | 3 | 3 | 27 | Secuirty Leader | 2023-10-24 | Enforce a secure password policy | Ok, hasing is implemented using bcrypt | Closed
Securty | SQL Injection | SQL injection is a tactic involving malicious SQL code input to manipulate and access a database. | 3 | 3 | 3 | 27 | Secuirty Leader | 2023-10-24 | Mitigate SQL Injection attacks by employing input validation and utilizing parameterized queries. | Ok, injections are prevented using sanitize filter | Closed
Communication | duplicate work | Team members unknowingly work on the same tasks | 3 | 3 | 2 | 18 | Team Leader | 2023-10-24 | Establish better communication channels | Ok, no duplicate work so far | Closed
Technology competence | Not familiar with unit testing | Team members may lack experience in unit testing | 2 | 3 | 3 | 36 | QA leader | 2023-10-24 | Provide unit testing training and guidance | Ok, no major bottlenecks so far | Closed
Technology competence | Not familiar with the framework used | Team members may lack familiarity with the framework | 3 | 4 | 3 | 18 | Design leader | 2023-10-24 | Provide training on the framework, mentorship | Ok, no major problems with framework | Closed
Technology competence | Not familiar with the programming language used | Team members may lack familiarity with the programming language | 3 | 4 | 3 | 18 | Design leader | 2023-10-24 | Provide training on the programming language | Ok, no major problems with language | Closed
Management | scope creep | The project scope may expand beyond the original plan | 3 | 4 | 3 | 18 | Team Leader | 2023-10-24 | Implement strict change control processes | Ok, no scope creep | Closed
Technology competence | Other technology incompetence | Other technology-related challenges may arise | 3 | 3 | 2 | 18 | Design leader | 2023-10-24 | Address specific challenges as they arise | Ok, no unmanagable challenges | Closed
Technology competence | Not familiar with Git | Team members may not be familiar with Git | 2 | 3 | 3 | 36 | Configuration leader | 2023-10-24 | Provide Git training and establish best practices | Ok, problems with git are resolved continuously | Closed
Communication | Lack of motivation or responsibility | Team members may lack motivation or responsibility | 3 | 5 | 3 | 9 | Team Leader | 2023-10-24 | Implement motivation strategies, set clear goals | Ok, projected is successfully completed despite problems | Closed
Management | improper planning | Inadequate project planning and scheduling | 4 | 3 | 3 | 18 | Team Leader | 2023-10-24 | Review and update project plan and schedule | Ok, projected is successfully completed despite problems | Closed
Design and implementation | improper technology stack | Inappropriate technology stack selection | 3 | 4 | 3 | 18 | Design leader | 2023-10-24 | Review and align technology stack with project goals | Ok, technology stack is suitable | Closed
Testing | Incomplete test model | Not all critical aspects of the system are tested | 3 | 4 | 3 | 18 | QA leader | 2023-10-24 | Review test coverage, identify gaps, and create new tests | Ok, there are no critical or major bugs | Closed
Devops | Broken deployment | Failure to successfully deploy application to production | 2 | 5 | 3 | 12 | Configuration leader | 2023-10-24 | Continuous deployment and deployment logs | Ok, vercel and CI tools help to keep build healthy | Closed