## Summary-GroupIterationProgress
This report has 1 group iteration progress summary sheet to be filled at the end of each iteration by the team leader, 1 project ontribution sheet to be filled by everyone at the end of the semester, and 1 weekly report sheet per student.
iteration | Date range | accomplishment summary (such as user stories/tasks completed/big progress, good practices used, etc) | Technical issues summary | non-technical issues summary | Process improvement/plan | # of user story points completed | # of user story points in progress | # of issues opened | # of issues closed | # of issues remained | Total work time (h) | Total Individual work time (h) | Total group meeting time (h) | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | Code coverage | Test pass rate | Defect rate
0 | 09/05 - 09/14 | We decided on the kind of application we needed to create |  | Team-members changing constantly. Makes it difficult to properly plan. | As the teams should be set by now this should be resolved and we will try to meet regularly to being the project | 0 | 0 | 0 | 0 | 0 | 55 | 10 | 8 | 10 | 7 | 5 | 0 | 0 | 11 | 2 | - | - | -
1 | 09/14 - 09/26 | Application setup, Sign In/SignUp created. Vercel integration. | Mid-testing mongoDB connection failed after developers had signed off-line. Possibly a version issue. | Struggling to have teammembers participate in meetings, which in turn leads to confusion and lack of direction. | Try to stress the importance of being present during meetings. Possibly reschedule meeting times and try to facilitate a better work flow. | 30 | 30 | 0 | 0 | 0 | 144 | 29 |  | 28 | 14 | 12 | 31 | 7 | 11 | 8 | Unit test: 15% E2e test: 0% | 100% | 0
2 | 09/27 - 10/10 | We worked on many user stories involving the development of the site. We have completed most of the backend and will finish the UI in the future. We also have all contributed to refactoring of the code when possible. |  | Still struggling with communication, but to a lesser degree | Team has been working together to communicate better. | 19 | 11 | 0 | 0 | 0 | 150 | 25 | 5 | 20 | 10 | 15 | 60 | 30 | 10 | 5 | Unit test: 11% E2e test: 62% | 100% | 0
3

## projectcontribution
This sheet need to be filled by the end of the semester. You should clearly describe your contribution to the group project in each category in the whole semester.
StudentName | SPPP Document | Requirement Analysis on Pivotaltracker | Design Document (SDD) | Testing Documentation (STD) | Presentation | Implementation (code on Github) | Testing (unittest code on Github or manual testing) | Configuration and Deployment | General communication and management | Other Comments

## Devon Dudley
Your Lead Roles: QA Lead and Design and Implementation Lead
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05 - 09/12 | 14 | 11 | 3 | 0 - learn git and django, read several tutorials 1 - define high level requirements, 2 - Creating UI/UX design in Figma 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 4 | 3 | 2 | 0 | 0 | 1 | 1 | 0 | 1. Write 3 sections of SPPP 2. Set up git, commit a test message on git 3. Participate in Iteration 0 presentation | 1. Communication is not clear. Task assignments is not clear. 2. Team has had multiple changes in the first week. 3. Different levels of experience with going through the life-cycle of a build. | 1. finish Django tutorial in 2 weeks, be able to create simple Djano hello world project next week 2. Send task assignments to all members again | 0 - Finish Figma design 1 - Start outlining components 3 - Start coding the frontend 4 - Implement Jest and create test cases | 10
2023-02-03 | 09/13 - 09/26 | 18 | 14 | 4 | 0 - Creating UI/UX design in Figma 2 - Edit SDD document 3 - Edit STD document 4 - Sign-in/sign-up Testing | 8 | 5 | 0 | 1 | 0 | 0 | 0 | 0 | 1. Write sections of SDD 2. Write sections of STD 3. Finish and adjust design 4. Testing | 1. Communication suffers 2. Insufficient planing | 1. No plan 2. Task tracker is ignored by the team, no plan | 0 - Finish home screen 1 - Testing 2 - Update documents | 10
4 | 09/27 - 10/03 | 35 | 33 | 2 | 0 - Home screen 1 - Testing | 23 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 1. Home Screen 2. Kinda testing | 1. Communication suffers 2. Insufficient planing 3. Distribution of work 4. People working on the same deliverables | 1. No plan 2. Task tracker is ignored by the team, no plan 3. Tasks are falling behind | 0 - Home screen - Effects 1 - User Settings 2 - Testing | 30
5 | 10/03 - 10/10
6 | 10/10 - 10/17
7 | 10/17 - 10/24

## Alisa Belousova
Your Lead Roles: Configuration Lead
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05 - 09/12 | 10 | 9 | 1 | 0 - learn project requirements 1 - risk management, tools 5 - 2 calls, discord 6 - set up git | 1 | 5 | 0 | 0 | 0 | 2 | 1 | 0 | 1. Write risk management 2. Write tools section of SPPP 3. Set up git, create initial project setup commit | 1. Communication suffers 2. Many changes within the team 3. Insufficient planing | 1. Better planning and 2 calls per week instead of 1 should make the situation better 2. Hopefully no more changes 3. Suggest to actually use task tracker for planning | 1. Add github actions 2. Make deployment 3. Setup database 4. Help team members with project setup 4. Planning | 10
2 | 09/13 - 09/19 | 11 | 9 | 2 | 5 - help team members with the project, discussing what needs to be done or fixed 6 - setup CI/CD, tests, code quality tools | 0 | 0 | 0 | 0 | 0 | 3 | 6 | 0 | 1. Continuous deployment 2. Setup code quality tools check and test run in PR 3. DB setup | 1. Communication suffers 2. Insufficient planing | 1. No plan 2. Task tracker is ignored by the team, no plan | 1. Fix security problems 2. Update documentation 2. Backend | 10
3 | 09/20 - 09/26 | 12 | 10 | 2 | 1 - write SPPP 4 - setup test infrustructure and write sample tests | 0 | 8 | 0 | 0 | 2 | 0 | 0 | 0 | 1. Rewritten SPPP and other docs 2. First tests writeen | 1. Communication suffers 2. Insufficient planing | 1. No plan 2. Task tracker is ignored by the team, no plan | 1. Update documentation | 10
4 | 09/27 - 10/03 | 12 | 11 | 1 | 1 - update SPPP and risks, write STD and SDD, fix other docs 3 - code review | 0 | 10 | 0 | 1 | 0 | 0 | 0 | 0 | 1. Updated SPPP, risks, SDD and STD and other docs | 1. Communication suffers 2. Insufficient planing | 1. No plan 2. Task tracker is ignored by the team, no plan | 1. Update documentation | 10
5 | 10/04 - 10/10 | 15 | 14 | 1 | 1 - update SPPP and risks, write STD and SDD, fix other docs 3 - code review 6 - coverage | 0 | 10 | 0 | 2 | 0 | 0 | 2 | 0 | 1. Updated SPPP, risks, SDD and STD and other docs | 1. Communication suffers 2. Insufficient planing | 1. No plan 2. Task tracker is ignored by the team, no plan | 1. Update documentation 2. Write tests | 10
6 | 10/11- 10/17
7 | 10/18 - 10/24

## Nick Cruz
Your Lead Roles: Team Leader, Requirement leader
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05 - 09/12 | 21.5 | 18.5 | 3 | 0 - learn git, read several tutorials 1 - define high level requirements, 2 - determined pages and drafted application design in Figma 5 - make project plan, send reminders to team members 6 - set up git 7 - research similar products, prepare presentation | 1 | 1 | 3 | 0 | 0 | 10 | 0.5 | 3 | 1. Reviewed and rewrote SPPP 2. Set up git, commit a test message on git 3. Created the presentation 4. Created wireframes for the project | 1. Team member changes. This makes it difficult as those who joined late were unable contribute much early. I was one of the few people involved for the entire assigned time. I assumed role of team leader after the former leader left the team due to being here for the current duration. 2. Sending many reminders about simple things (like submitting lab1 or this progress report) when those are things members should be keeping up for on their own. | 1. Unlikely people will be coming or going, so this issue should resolve itself. 2. If this continues will talk to the team about ensuring that their individual assignments are not my responsibilities and that they need to focus on completing those themselves. | 1. Begin work on the application by working on the sites needed. 2. Ensure there is communication between all members and assist them and provide support as necessary. | 20 hours
2 | 09/13 - 09/19 | 10 | 9 | 1 | 0 - learn what NextJS, Jira, Vercel is. Read through NextJS tutorial and explored Jira.. 1 - Created Jira stories and moved them forward 5 - Coordinated meetings, determined delegated tasks 6 - Researched and discussed web hosting platform | 6 | 1.5 | 0 | 0 | 0 | 1 | 0.5 | 0 | 1. Created and moved along some Jira stories 2. Locally set up inital project pulled from Git | 1. Could not set up a meeting where all team members could attend. The time difference makes it difficult to have calls at convenient hours. 2. Unfamiliar with responsibilities as requirement leader. I originally requested development lead as I that is the only role I have experience in for this field. | 1. Establishing a norm for team meetings that is convenient for all team members (after class, weekend afternoons). 2. I did a lot of research this week to understand my role better. | 1. Provide support to development team to ensure progress on the deliverables 2. Reviewing code being worked on 3. Updating the Jira board 4. Determine assignee for Iteration 1 submission documentations 5. Get status updates on tasks completed, and tasks that still need to be done. | 20 hours
3 | 09/20 - 09/26 | 20 | 18 | 2 | 1 - Completed presentation and presentation video, reviewed and edited documentations 4 - Validated developed features 5 - Coordinated meetings, ensured requirements were met 6 - Deployed Iteration 1 features locally | 0 | 9 | 0 | 0 | 4 | 3 | 2 | 0 | 1. Completed presentation and presentation video 2. Reviewed implemented code - Password needs to be hashed after submit button, before sending to backend - Need to check email is an email format - No need the HelloWorld page, the / should show the /signin content - Rounded Sign in, but not rounded Signup - Consolidate Car Information with Edit Car for now (separate if have time) - Linting is failing 3. Reviewed completed documentations 4. Worked on STD documentation and testing. | 1. Did not get a final status of Iteration 1 until the night before due date. 2. Current Jira stories are too large to complete in 1 week. It took the whole iteration instead. 3. PRs are not being created incrementally. Could only review code at the end of the iteration. 4. PRs created are not being reviewed and could not be merged. 5. Still difficult to meet with all team members. No communication when work cannot be completed on time and responsibilities are being shifted without discussion and lack of consideration. 6. Due to lack of communication and last minute dialogue, no issues were able to be opened or reviewed or resolved at this time. | 1. Need to enforce meeting attendance, or call out missing attendees to update via Discord. 2. Voice what I need to know to set up stories myself with smaller scope. Request team members to move stories along. 3. Create a PR for each story to minimize PR scope and continuous code deployments. 4. Discuss how to deploy to Vercel. Request team members to review and approve PRs to ensure code is updated. 5. Set deadlines for when work needs ot be completed ahead of time. Reassign work if it has not been completed and hold team members accountable. Discuss that work is not to be reassigned to other individuals without prior consent. | 1. I would like to be involved with development, so I will be requested to do the Add Car implementation. Next week I will focus on the backend routing and configuration for the Add Car endpoint. 2. Set up a meeting to discuss work in detail and create stories for all team members to be completed by week instead of Iteration. | 30 hours
4 | 09/27 - 10/03 | 30 | 29.5 | 0.5 | 0 - Refactoring techniques 3 - Refactored much of the login page 4 - implemented unit testing in login 5 - delegated tasks and set meetings 6 - deployed refactored changes | 3 | 0 | 0 | 15 | 10 | 1.5 | 0.5 | 0 | 1. Created and moved along some Jira stories 2. Worked on learning best way to refactor/ bugfix login page credential check. 3. Implemented refactored changes to login/signup page. 4. Implemented unit test for the login page and ensured they worked. | 1. Communication is still a problem. People missing meetings | 1. Was able to get into contact with all members and set a new meeting time, along with understand why the previous meeting time did not work. In addition, spoke to all members about the importance of meetings and attendance. | 1. Work on Maintenance page backend to be more involved in programming aspect. 2. Moving stories along and creating new stories as needed. | 20 hours
5 | 10/04 - 10/10 | 30 | 29.5 | 0.5 | 0 - Learning mongoDB and Next 3 - Created and worked on backend of the add/edit/maintenance 4 - Testing use cases and edge cases 5 - Communicating with team about what to accomplish and work on | 4 | 0 | 0 | 20 | 5 | 1.5 | 0 | 0 | 1. Created and worked on backend for add/edit/maintenance pages. | 1. Did not expect to have to implement the back end for the add/edit car. 2. Was difficult to properly set up the backend and took a long time to properly set everything up. | 1. Should be more clear about what people are expected to complete. | 1. Finishing touches/additional features for the application. | 20 Hours
6 | 10/11- 10/17
7 | 10/18 - 10/24

## Chenghao Ye
Your Lead Roles: Design and Implementation Lead
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05 - 09/12 | 4.5 | 3 | 1.5 | 0 - learn git 5 - Communicate about project idea 6 - set up git | 1 |  |  |  |  | 1 | 1
2 | 09/13 - 09/19 | 30 | 28 | 3 | 0 - Review React, learn next.js, Typescript 2 - Designing frontend components 3- Implement Console Page, components, add cars, maintenance 5 - Communicate about backend details with team members in order to design frontend | 12 |  | 4 | 12 |  | 2
3 | 09/20 - 09/26 | 12 | 11 | 1 | 0 - Learn unit test 2 - Designing frontend components 3- Implement Console Page, components, 5 - Communicate about backend details with team members in order to design frontend | 2 |  | 2 | 6 |  | 1
4 | 09/27 - 10/03 | 33 | 30 | 3 | 0 - Learn Jest 1 - Refractor 2 - Designing SideBar and Form component, CarInfo.tsx, 3- Implement SideBar and Form component, CarInfo.tsx, and fix AddCar.tsx 5 - Communicate about backend details about Form and Submit 6 - Eslint | 2 | 3 | 4 | 10 |  | 8 | 3
5 | 10/04 - 10/10
6 | 10/11- 10/17
7 | 10/18 - 10/24

## Cangqing Wang
Your Lead Roles: security
Week # | Date range | Total actual time of this week tasks (h) | Total Individual work time | Total group meeting time | Individual Task Breakdown 0 - learning 1 - requirement analysis 2 - design 3 - implementation 4 - test 5 - communication/management 6 - configuration/environment 7 - unclassified | time for type 0 tasks | time for type 1 tasks | time for type 2 tasks | time for type 3 tasks | time for type 4 tasks | time for type 5 tasks | time for type 6 tasks | time for type 7 tasks | Project Deliverable Contribution | Issues | Issue status or plan | Estimated tasks for next week | Total estimated time
1 | 09/05 - 09/12 | 13 | 11.5 | 1.5 | 0 - learning git command 2 - design project 3 - implementation 4 - test git command 5 - communication and discuss with team member 6 - push doc/read.me | 2 | 0 | 2 | 3 | 1 | 3 | 0.5 | 0
2 | 09/13 - 09/19 | 29 | 27 | 2 | 0 - Review React, learn next.js, Typescript 3- Implement Signin/up backend and frontend in Nodejs and Nextjs, jwt hash 4- manual test signup functiong with postman and nextauth api 5 - Communicate about backend details with team members in order to design frontend 7 - set up mongoDB, model schema, .env security file, build enviroment, | 6 | 0 | 0 | 12 | 1 | 2 | 0 | 6 | 1. implemented backend with Node.js and another version Next.js Api for team choose 2. implemented signin/up frontend form 3. use moogoose initial User database schema | 1. lack of discuss stack side, was not clear what tech stack should we use. 2. unfamiliar with github delete commit/ merge request requirement | 1. Should have more group meeting |  | 2
3 | 09/20 - 09/26 | 16.1 | 14.1 | 2 | 3 - implementation and connect backend with frontend, dashboard, fix CSS, main page 4 - manual test 5 - communicate with team member about testing build 7 - signin page detailing (css) dashboard page's onclick() function, next Link setup, login Session | 0 | 0 | 5.5 | 0 | 1 | 2 | 0 | 5.6 |  | 1. Getting dashboard frontend into main project, test. 2. fix session proble(user can visit dashboard without session) | 1. Get main page done |  | 10
4 | 09/27 - 10/03 | 23 | 21 | 2 | 0 - Learning Playwright Test Case 3 - Re-wirte css and refactor, 2 versions of Maintenance Page & Edit Maintenance page inc. Calendar, Add Car & Car Information Page 4 - manual test 5 - communicate with team member about refactoring and re-write CSS | 6 | 0 | 0 | 10 | 1 | 4 | 0 | 0 | 1. refactory Add/Edit Page, add Maintenance Page and Calendar View | N/A | N/A | Connect Frontend and Backend on Maintenance Pages | 10
5 | 10/04 - 10/10 | 16.5 | 14.5 | 2 | 3. Implemented ManageCar, CarInfo, Edit/Addt Car working with backend & DB |  |  |  | 14.5
6 | 10/11- 10/17
7 | 10/18 - 10/24