## Sheet1
Risk Category | Risk Title | Description | Estimated likelihood of occurrence (L: 1-5 with 1 lowest likelihood) | Estimated Impact (I:1-5 with 1 lowest impact) | Estimated retirement Cost (C: 1-5 with 1 lowest cost) | Priority (lowest number has high priority) (6-L)*(6-I)*C) | Responsible engineer | Target completion date | Detailed plan | Execution summary | Status
Devops | Database failure | Database corruption or unavailability | 4 | 5 | 5 | 10 | Configuration leader | on going- as needed | Setup recovery strategy |  | Open
Devops | Broken deployment | Failure to successfully deploy application to production | 2 | 5 | 3 | 12 | Configuration leader | on going- as needed | Continuous deployment and deployment logs |  | Open
Technology competence | Not familiar with Git | Team members may not be familiar with Git | 2 | 3 | 3 | 36 | Configuration leader | on going- as needed | Provide Git training and establish best practices |  | Open
Design and implementation | Messy code | Codebase may become disorganized and hard to maintain | 3 | 3 | 2 | 18 | Design leader | on going- as needed | Enforce coding standards, conduct code reviews |  | Open
Technology competence | Other technology incompetence | Other technology-related challenges may arise | 3 | 3 | 2 | 18 | Design leader | on going- as needed | Address specific challenges as they arise |  | Open
Design and implementation | improper technology stack | Inappropriate technology stack selection | 3 | 4 | 3 | 18 | Design leader | on going- as needed | Review and align technology stack with project goals |  | Open
Technology competence | Not familiar with the framework used | Team members may lack familiarity with the framework | 3 | 4 | 3 | 18 | Design leader | on going- as needed | Provide training on the framework, mentorship |  | Open
Technology competence | Not familiar with the programming language used | Team members may lack familiarity with the programming language | 3 | 4 | 3 | 18 | Design leader | on going- as needed | Provide training on the programming language |  | Open
Testing | Incomplete test model | Not all critical aspects of the system are tested | 3 | 4 | 3 | 18 | QA leader | on going- as needed | Review test coverage, identify gaps, and create new tests |  | Open
Technology competence | Not familiar with unit testing | Team members may lack experience in unit testing | 2 | 3 | 3 | 36 | QA leader | on going- as needed | Provide unit testing training and guidance |  | Open
Requirements | constant requirements changes | Frequent changes in project requirements | 4 | 4 | 3 | 12 | Requirement leader | on going- as needed | Implement a change request process, assess impact |  | Open
Design and implementation | Improper design | Design choices may not align with project goals | 3 | 3 | 2 | 18 | Requirement leader | 2023-09-26 | Review and refine design, involve stakeholders |  | Open
Requirements | unclear requirements | Project requirements may be unclear or ambiguous | 4 | 3 | 3 | 18 | Requirement leader | on going- as needed | Collaborate with stakeholders to clarify requirements |  | Open
Secuirty | Weak password | Predictable passwords can pose authentication vulnerabilities, making it easier for attackers to target specific users. | 3 | 3 | 3 | 27 | Secuirty Leader | on going- as needed | Enforce a secure password policy |  | Open
Secuirty | Brute force attack | A brute-force attack aims to access a system or user account by trying numerous random username and password combinations until a successful one is discovered. | 3 | 3 | 3 | 27 | Secuirty Leader | on going- as needed | Implement a reliable brute-force protection system |  | Open
Security | Poor Session Management | Various session mismanagement vulnerabilities exist, including the absence of session timeouts, session cookies lacking the Http-Only flag, and inadequate session invalidation. | 3 | 3 | 3 | 27 | Secuirty Leader | on going- as needed | Utilise proper session invalidation strategies. |  | Open
Securty | SQL Injection | SQL injection is a tactic involving malicious SQL code input to manipulate and access a database. | 3 | 3 | 3 | 27 | Secuirty Leader | on going- as needed | Mitigate SQL Injection attacks by employing input validation and utilizing parameterized queries. |  | Open
Management | lack of management skills | Project managers may lack essential management skills | 3 | 4 | 2 | 12 | Team Leader | on going- as needed | Provide management training and support |  | Open
Communication | worked on wrong components | Team members work on the wrong project components | 2 | 4 | 2 | 16 | Team Leader | on going- as needed | Improve project component tracking |  | Open
Communication | Lack of motivation or responsibility | Team members may lack motivation or responsibility | 3 | 4 | 3 | 18 | Team Leader | on going- as needed | Implement motivation strategies, set clear goals |  | Open
Communication | duplicate work | Team members unknowingly work on the same tasks | 3 | 3 | 2 | 18 | Team Leader | on going- as needed | Establish better communication channels |  | Open
Management | scope creep | The project scope may expand beyond the original plan | 3 | 4 | 3 | 18 | Team Leader | on going- as needed | Implement strict change control processes |  | Open
Management | improper planning | Inadequate project planning and scheduling | 4 | 3 | 3 | 18 | Team Leader | on going- as needed | Review and update project plan and schedule |  | Open
Communication | useless work | Team members may perform work that isn't needed | 3 | 2 | 2 | 24 | Team Leader | on going- as needed | Clearly define project requirements and goals |  | Open
Personel | Loss of team members | One or more team members drop the class | 2 | 4 | 4 | 32 | Team Leader | 2023-09-12 | Redefine the project scope if necessary, and assign the tasks to other team members. | Lauren was moved to team 7, Abdallah left the course | Open